## CbC to EC010024979
| CbC to EC010024979 |  |  |  |  | Supplier fill here |  |  |  | Train Manufacturer Comments
Absolute Number | Req. ID | Section | Requirement Text | Object Type | Validation Method | Compliance Status | Compliance Argument | Satisfying Document | Validation Evidence | Acceptance | Acceptance Date | Train Manufacturer Comments
2211 |  |  | 1 Introduction
2803 |  | 1 Introduction | The purpose of this specification is to define the technical, quality, functional, performance, Reliability, Maintainability, Availability, Safety (RAMS) requirements in order to allow the Supplier to carry out the design, construction, qualification and certification/type approval of the Coupling System requested in compliance with the applicable international standards and with the explicit requirements stated in this document. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2804 |  | 1 Introduction | In addition to SyRS, during design phases Hitachi Rail STS will provide and share with the Supplier the following documents in order to assure the right functional integration of the system into the vehicle: Functional Requirements Specification (FRS). Interface Control Document (ICD). | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2805 |  | 1 Introduction | The FRS will include detailed functional requirements to allow the development of the related function of the system under scope (mostly impacting but not limited to the system’s SW). | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2806 |  | 1 Introduction | The ICD will include the details of the mechanical, electrical and network interfaces of the system under scope to any other affected item. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2807 |  | 1 Introduction | Both the FRS and ICD will be issued during or after the PDR and they can be updated up to the Design Freeze Phase (DFP) that will occur after the Final Design Review (FDR) acceptance with Customer, based on the delivery plan to be defined by Hitachi. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2808 |  | 1 Introduction | Until DFP the supplier shall implement and validate the FRS and ICD requirement by the system/SW without any additional cost. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2809 |  | 1 Introduction | After DFP and up to the end of the vehicle level qualification tests, the updated FRS and ICD will be shared and agreed between the supplier and Hitachi. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2810 |  | 1 Introduction | 1.1 Scope of supply | Heading
2811 | HR-SyRS-TMP-00001 | 1.1 Scope of supply | The scope of Supply shall be based on the following list: The system required in this specification and all the hardware and software parts that are necessary to guarantee the functionalities and performances required by this SyRS and the attached regulations; The design activities for the system under scope of supply; The system configuration management; PTU, BTE and special tools; All the required contractual documentation (CDRLs); Validation and type testing activities; Support for validation of the system at train level. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2812 |  | 1 Introduction | 1.2 Definitions | Heading
2813 |  | 1.2 Definitions |  | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2814 |  | 1 Introduction | 1.3 Acronyms and abbreviations | Heading
2815 |  | 1.3 Acronyms and abbreviations |  | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2212 |  |  | 2 Reference standards and documents
2816 |  | 2 Reference standards and documents | The priority order of the following documents has to be intended as follows: · Last revision of this document; · Contractual documents at latest revision applicable; · Applicable standards; · HR internal standards | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2817 |  | 2 Reference standards and documents | In case of any conflict between these documents, the most restrictive requirements shall be considered. In case of requirements incompatibility, the priority shall be stated with the On-Board System Engineering department. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2818 |  | 2 Reference standards and documents | 2.1 Customer documents | Heading
2819 |  | 2.1 Customer documents | Customer documents | View Reference |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2820 |  | 2 Reference standards and documents | 2.2 Hitachi documents | Heading
2821 |  | 2.2 Hitachi documents | SRD Template_Hitachi documents | View Reference |  |  | 2024-04-17 / tmdcth / Wiegand Noted
3075 |  | 2.2 Hitachi documents | The documents referenced in the table below are intended as the latest revision released in the G-PLM data management system. | Heading
2822 |  | 2 Reference standards and documents | 2.3 Applicable standards | Heading
2823 |  | 2.3 Applicable standards | The following sections define the applicable standards. They shall be assumed at the latest issue available referred to the NTP date except to as differently stated by this documentation or the documents at §2.1. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2824 |  | 2.3 Applicable standards | 2.3.1 General standards | Heading
2825 |  | 2.3.1 General standards | General standards | View Reference |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2826 |  | 2.3 Applicable standards | 2.3.2 System specific applicable standards | Heading
3047 |  | 2.3.2 System specific applicable standards |  | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2213 |  |  | 3 Train Description
2828 |  | 3 Train Description | 3.1 General characteristics | Heading
2829 |  | 3.1 General characteristics | The Supplier shall design systems and components included in the Scope of Supply on the basis of the following vehicle’s general characteristics. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2830 |  | 3.1 General characteristics |  | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2831 |  | 3 Train Description | 3.2 Specific characteristics | Heading
2832 |  | 3.2 Specific characteristics | The Supplier shall consider the following specific vehicle characteristics for the design of the system and components included in the Scope of Supply. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2833 |  | 3.2 Specific characteristics |  | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2214 |  |  | 4 Operational Scenario
2834 |  | 4 Operational Scenario | 4.1 Environmental conditions | Heading
2835 |  | 4.1 Environmental conditions | 4.1.1 Temperature | Heading
3076 | EU-MAS-B02-CCO-00001 | 4.1.1 Temperature | Air temperature external to vehicle: Class T1 according to EN 50125-1, paragraph 4.3, Table 2. | Requirement | Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2836 |  | 4.1 Environmental conditions | 4.1.2 Humidity | Heading
3077 | EU-MAS-B02-CCO-00002 | 4.1.2 Humidity | In accordance with EN 50125-1 paragraph 4.4. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2837 |  | 4.1 Environmental conditions | 4.1.3 Wind | Heading
3078 | EU-MAS-B02-CCO-00003 | 4.1.3 Wind | In accordance with EN 50125-1 paragraph 4.5.1 | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2838 |  | 4.1 Environmental conditions | 4.1.4 Rain, snow, ice | Heading
3079 | EU-MAS-B02-CCO-00004 | 4.1.4 Rain, snow, ice | In accordance with EN 50125-1 paragraphs 4.6, 4.7 and 4.8. For snow we need to consider class S2 as per EN 20125-1. | Requirement | Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand In case of snow and ice accumulations on the coupler, kinematics and other movable parts, automatic functions can be reduced or inoperable. It can be necessary to remove ice and snow manually to restore the automatic functions. Optionally existing heating elements are not designed to melt severe accumulations of snow. No specific test planned. Existing test of equivalent design with C.o.C may be provided.
2839 |  | 4.1 Environmental conditions | 4.1.5 Altitude | Heading
3080 | EU-MAS-B02-CCO-00005 | 4.1.5 Altitude | Altitude class above the sea level: class A2 according to the EN 50125-1 paragraph 4.2, table 1. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2840 |  | 4.1 Environmental conditions | 4.1.6 Solar radiation | Heading
3081 | EU-MAS-B02-CCO-00006 | 4.1.6 Solar radiation | In accordance with EN 50125-1 paragraph 4.9 Classes R2 | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2841 |  | 4.1 Environmental conditions | 4.1.7 Lightning | Heading
3082 | EU-MAS-B02-CCO-00007 | 4.1.7 Lightning | In accordance with EN 50125-1 paragraph 4.10 | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but no specific test planned. Existing test of equivalent design with C.o.C may be provided.
2842 |  | 4.1 Environmental conditions | 4.1.8 Pollution | Heading
3083 | EU-MAS-B02-CCO-00008 | 4.1.8 Pollution | In accordance with EN 50125-1 paragraph 4.11 | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand Compliant. Existing test of equivalent design with C.o.C may be provided. with requirement, but no specific test planned
2843 |  | 4 Operational Scenario | 4.2 Installation conditions | Heading
2844 |  | 4.2 Installation conditions | The system, object of Supply, will be installed [to be specified the installation position of the system]. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2845 |  | 4.2 Installation conditions | 4.2.1 Water tightness | Heading
2846 | HR-BP-WPC08-ACO-00004 | 4.2.1 Water tightness | The supplier shall design the system taking into account that it shall be subjected to water test with the following parameters: | Requirement |  | Not compliant | 2024-04-17 / tmdcth / Wiegand No specific test planned.. Existing test of equivalent design with C.o.C may be provided.
2847 | HR-BP-WPC08-ACO-00005 | 4.2.1 Water tightness | The drainage concept shall be agreed with HR during the Design Review without additional costs. | Requirement |  | Partially Compliant | 2024-04-17 / tmdcth / Wiegand Compliant with requirement, but exclusion of additional costs is limited to components which will be designed project specific anyhow.
2848 |  | 4.2 Installation conditions | 4.2.2 Degrees of protection (IP) | Heading
2849 | EU-MAS-C08-GLY-00012 | 4.2.2 Degrees of protection (IP) | The Supplier shall refer to EN 60529 [3.5] in terms of definition of IP degree of protection. The following minimum degree of protection (except if it is specified in the present document) shall be fulfilled: Outdoor application: IP67 Outdoor application covered: IP55/IP65 according to component criticality level Indoor closed operating areas according to EN 50153 IP2x Accessible for passengers and in driver desk IP54 The only exception shall be for boxes requiring natural ventilation: for these boxes, the water tightness test shall be considered valid. | Requirement | Analysis Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand Compliant except for electric coupler: e-coupler IP grade is IP54 in uncoupled and IP55 in coupled condition. No specific test or analysis planned. Existing test of equivalent design with C.o.C may be provided.
2850 |  | 4.2.2 Degrees of protection (IP) | Alternative degrees of protection may be proposed to HR approval, based on the installation analysis and service proven solutions. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2852 |  | 4.2 Installation conditions | 4.2.3 Shock and vibration | Heading
2853 | HR-BP-WPC04-00246 | 4.2.3 Shock and vibration | The environmental shock and vibration level applied to the system/equipment, when the train is in operation, shall be compliant to EN 61373 [3.9]. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2854 | HR-BP-WPC04-00247 | 4.2.3 Shock and vibration | The functionality and the mechanical integrity of the system/equipment shall be tested in accordance to EN 61373 [3.9]. | Requirement |  | Partially Compliant | 2024-04-17 / tmdcth / Wiegand A specific test for this coupler is not considered in the commercial offer. We provide reference test and propose a service proven design. If required to repeat the test with this specific design, the offer can be updated.
2856 |  | 4.2 Installation conditions | 4.2.4 Structural strength and crashworthiness requirements | Heading
2857 | HR-BP-WPB15-00001 | 4.2.4 Structural strength and crashworthiness requirements | The system shall be compliant with the attached document [2.12]. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Attachemt unknown, please provide
2858 |  | 4.2 Installation conditions | 4.2.5 Aerodynamics and pressure requirements | Heading
2859 |  | 4.2.5 Aerodynamics and pressure requirements | 4.2.5.1 Category 1 vehicles | Heading
2860 |  | 4.2.5.1 Category 1 vehicles | 4.2.5.1.1 Definition | Heading
2861 |  | 4.2.5.1.1 Definition | Vehicles with a maximum speed up to and including 200 km/h and operating on a restricted network defined by: a) line sections with or without tunnel and maximum line speed up to and including 200 km/h; b) all line sections without tunnels and maximum line speed above 200 km/h up to and including 300 km/h; c) line sections with exclusively single-track tunnels and maximum line speed above 200 km/h up to and including 300 km/h. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2862 |  | 4.2.5.1 Category 1 vehicles | 4.2.5.1.2 Exceptional loads | Heading
2863 | EU-MAS-B12-REQ-00001 | 4.2.5.1.2 Exceptional loads | Loads specified in this section shall be combined with the vertical load defined in EN 12663 § 6, using the exceptional payload defined in EN 12663, Table 1. The resulting load shall be verified as mandated by EN 12663, § 5 for exceptional loading conditions. The load shall be applied as a uniform pressure on the whole surface of the carbody / component / equipment, positive pressure defined as acting from the inside to the outside of the carbody / component / equipment. The load shall be chosen according to the list below. 1. Component / systems placed on the boundary between the carbody and the outside, e.g., carbody structure, windows, doors, gangway Load value : ±1900 Pa 2. Component / systems placed outside the carbody, e.g., fairings, coupler doors, access hatches, equipment boxes. Load value : ±1900 Pa 3. Component / systems placed on the boundary between the carbody and the outside, e.g., carbody structure, windows, doors, gangway Load value None | Requirement |  | Partially Compliant | 2024-04-17 / tmdcth / Wiegand as far as applicable for couplers
2864 |  | 4.2.5.1 Category 1 vehicles | 4.2.5.1.3 Fatigue loads | Heading
2865 | EU-MAS-B12-REQ-00002 | 4.2.5.1.3 Fatigue loads | The load shall be applied according to the table below. Loads specified in this section shall be combined with the vertical load defined in EN 12663 § 6, using the normal payload defined in EN 12663, Table 1. The resulting load shall be verified as mandated by EN 12663, § 5 for fatigue loading conditions. The load shall be applied as a uniform pressure on the whole surface of the carbody / component / equipment, positive pressure defined as acting from the inside to the outside of the carbody / component / equipment. The load shall be applied according to the list below. 1. Component / systems placed on the boundary between the carbody and the outside, e.g., carbody structure, windows, doors, gangway Load value : ±800 Pa for 107 cycles 2. Component / systems placed outside the carbody, e.g., fairings, coupler doors, access hatches, equipment boxes. Load value : ±800 Pa for 107 cycles 3. Component / systems placed on the boundary between the carbody and the outside, e.g., carbody structure, windows, doors, gangway Load value None | Requirement |  | Partially Compliant | 2024-04-17 / tmdcth / Wiegand as far as applicable for couplers
2866 |  | 4.2.5 Aerodynamics and pressure requirements | 4.2.5.2 Category 2 vehicles | Heading
2867 |  | 4.2.5.2 Category 2 vehicles | 4.2.5.2.1 Definition | Heading
2868 |  | 4.2.5.2.1 Definition | Vehicles with maximum speed up to and including 200 km/h and use on all lines with a maximum line speed up to and including 300 km/h. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2869 |  | 4.2.5.2 Category 2 vehicles | 4.2.5.2.2 Exceptional loads | Heading
2870 | EU-MAS-B12-REQ-00003 | 4.2.5.2.2 Exceptional loads | TBD | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand compliance will be assessed if requirement is defined
2871 |  | 4.2.5.2 Category 2 vehicles | 4.2.5.2.3 Fatigue loads | Heading
2872 | EU-MAS-B12-REQ-00004 | 4.2.5.2.3 Fatigue loads | TBD | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand compliance will be assessed if requirement is defined
2215 |  |  | 5 Contractual Requirements
2873 | HR-SyRS-TMP-00097 | 5 Contractual Requirements | The supplier shall comply to all applicable requirements for the system as reported in this document. | Requirement |  | Not compliant | 2024-04-17 / tmdcth / Wiegand The compliance status to all applicable requirements in this document will be stated individually.
2874 | HR-SyRS-TMP-00098 | 5 Contractual Requirements | The supplier shall provide a list of the requirements that cannot be met (if any) and the related justification to HRI for further discussions | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2875 | HR-SyRS-TMP-00099 | 5 Contractual Requirements | The Customer and Hitachi requirements that cannot be met by the supplier, as agreed with HRI, are reported in the SyRS Appendix A - Not Compliant Requirements List. During CDR phase, HRI shall support the supplier to waive these requirements. In case the proposed not compliances should not be accepted by final Customer, HRI and the supplier shall work together in order to find an alternative acceptable proposal. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2216 |  |  | 6 System Architecture
2691 |  | 6 System Architecture | The current specification highlights requirements to be met by Coupling System of a high capacity EMU/BEMU train. The vehicle is characterized by an articulated layout, composed by 2 up to 4 cars. HR plans to install an automatic coupler at each free-end of the train. | Information |  |  | 2024-04-17 / tmdcth / Wiegand Noted
2217 |  |  | 7 System Requirements
2876 |  | 7 System Requirements | 7.1 General Requirements | Heading
2693 | HR-BP-WPD16-ML-IUC-00001 | 7.1 General Requirements | The coupling system shall consist of the following components: An automatic coupler for each cab-end of the train A rescue coupler (opt. one for each cab-end of the train) | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2694 |  | 7.1 General Requirements | AUTOMATIC COUPLER: | Information
2695 | HR-BP-WPD16-ML-IUC-00002 | 7.1 General Requirements | The automatic coupler shall be designed in accordance with TSI standards (Commission regulation no. 1302/2014 of 18 November 2014). | Requirement | Analysis Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2696 | HR-BP-WPD16-ML-IUC-00003 | 7.1 General Requirements | The automatic coupler shall be designed in accordance with EN16019 Railway applications - Automatic coupler. | Requirement | Analysis Demonstration Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand The position of the strain gauges in Schaku-tests may deviate from the examples given in section 5.
2697 | HR-BP-WPD16-ML-IUC-00004 | 7.1 General Requirements | The automatic coupler shall include at least the following components: Coupler head Scharfenberg® type 10 according to EN16019 Regenerative energy absorbing device. Self-centering device Vertical-supporting device Shear-off device Electrical head located above the mechanical head Air supply hoses and interfaces for MRP, UP and BP Cables to the car and relative connectors. Whatever else would be required to ensure proper operation of the system (as, for instance, cables, connectors, switches, hoses and whatever needed to wire and put the system into work) and to meet the contractual and normative requirements. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2698 | HR-BP-WPD16-ML-IUC-00005 | 7.1 General Requirements | To properly work at the temperatures specified in the reference standard, an adequate heating system shall be designed. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3124 | HR-BP-WPB02-00031 | 7.1 General Requirements | Central couplers shall be provided with a heating system to maintain the reliability of the automatic coupler even in cold and snowy weather conditions. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3125 | 33137.AA.853 | 7.1 General Requirements | The coupling head of automatic couplings is equipped with an end surface heater that defrosts the end surface during the preparatory service under the environmental influences present during operational use and the associated conditions of use. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3126 | 33137.AA.854 | 7.1 General Requirements | The couplings of the electrical connections of automatic couplings are equipped with a heating system that de-ices the couplings of the electrical connections during the preparatory service under the environmental influences present during operation and the associated conditions of use. | Requirement | Demonstration Test | Not compliant | 2024-04-16 / tmdcth / Wiegand: The heating is dimensioned to prevent the build-up of ice and snow but not to melt down large amounts of ice and snow in a acceptable.
2699 | HR-BP-WPD16-ML-IUC-00006 | 7.1 General Requirements | The automatic coupler shall be equipped with a cover that protects the mating face when not connected to another vehicle. | Requirement | Demonstration | Compliant | Clarification required: We offer the seperate front face cover used for Caravaggio/ROCK train couplers. Please confirm if this is expected or other type of cover is meant.
2700 | EU-MAS-D16-S_COUP-00001 | 7.1 General Requirements | The electrical head shall be equipped with the following contacts: 2 x 60 contacts (including 2 x 15 gold pins) 6 (3+3) connectors (Quintax or similar) equipped with 4 golden pins each | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2701 |  | 7.1 General Requirements | RESCUE COUPLER: | Information
2702 | HR-BP-WPD16-ML-IUC-00008 | 7.1 General Requirements | The rescue coupler shall be designed in accordance with TSI standards (Commission regulation no. 1302/2014 of 18 November 2014). | Requirement | Analysis Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2703 | HR-BP-WPD16-ML-IUC-00009 | 7.1 General Requirements | The rescue coupler shall be designed in accordance with EN15020 Railway applications - Rescue coupler. | Requirement | Analysis Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2704 | HR-BP-WPD16-ML-IUC-00010 | 7.1 General Requirements | The rescue coupler shall be provided with handles on both the sides to be lifted by two persons. | Requirement | Demonstration | Partially Compliant | deviations: - coupling in 150m radius might require manual adjustment, to be checked 2024-05-07 / tmdcth / Wiegand / update: - strength test might slightly differ from specifications in EN 15020 Mix-up with requirement of EN 16019 for automatic couplers. EN 15020 does not specifiy strain gauge positions
2705 | HR-BP-WPD16-ML-IUC-00011 | 7.1 General Requirements | The installation of the rescue coupler on the draw hook shall not require the screw coupling to be removed. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2706 | HR-BP-WPD16-ML-IUC-00012 | 7.1 General Requirements | The rescue coupler shall be equipped with quick couplings to connect the pneumatic flexible hoses to the coupler itself. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2877 |  | 7 System Requirements | 7.2 Performance Requirements | Heading
2878 | HR-SyRS-TMP-00012 | 7.2 Performance Requirements | The system, object of the Supply, shall guarantee the respect and the fulfilment of all the performance requirements outlined in the present SyRS. It is remarked that the fulfilment of the required performances in meant to be relevant of the complete system compliance to Hitachi requirements and integration at train level. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2708 |  | 7.2 Performance Requirements | GATHERING RANGE: | Information
2709 | HR-BP-WPD16-ML-IUC-00013 | 7.2 Performance Requirements | A guiding bar and a horn to maximize the gathering range shall be provided. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2710 |  | 7.2 Performance Requirements | MOVEMENTS: Please find below the maximum angles to be achieved during working operation. | Information
2711 |  | 7.2 Performance Requirements | AUTOMATIC COUPLER: | Information
2712 | EU-MAS-D16-S_COUP-00002 | 7.2 Performance Requirements | The automatic coupler shall be able to rotate according to the following angles with no damage to any part: | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2713 |  | 7.2 Performance Requirements | RESCUE COUPLER: | Information
2714 | EU-MAS-D16-S_COUP-00003 | 7.2 Performance Requirements | The rescue coupler shall be able to manage the following angles with no damage to any part: * The pitch angle might change depending on the length of the offered rescue coupler. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2715 |  | 7.2 Performance Requirements | ENERGY ABSORPTION: Please find below the expected performance in terms of regenerative (coupling) energy absorbing. | Information
2716 |  | 7.2 Performance Requirements | AUTOMATIC COUPLER: | Information
2717 |  | 7.2 Performance Requirements | The train is an articulated-type composed by up to 4 cars, as shown in the sketch below: The mass of each car is described in the following table: * ready for operation weight (tare + staff + consumables) | Information | Analysis |  | 2024-04-17 / tmdcth / Wiegand / noted
2024-04-17 / tmdcth / Wiegand / noted
2024-04-17 / tmdcth / Wiegand / noted
2718 | HR-BP-WPD16-ML-IUC-00016 | 7.2 Performance Requirements | The coupling scenario shall be considered as one train stopped and braked vs one train running at coupling speed (nominal and maximum). | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2719 | HR-BP-WPD16-ML-IUC-00017 | 7.2 Performance Requirements | The regenerative absorption device shall be preloaded, such that its activation occurs once a certain compression load is reached. | Requirement | Analysis | Not compliant | 2024-04-17 / tmdcth / Wiegand In accordance with other requirements we provide rubber cushion drawgear EFG3s which cannot have preload due to technical reasons.
2720 | HR-BP-WPD16-ML-IUC-00018 | 7.2 Performance Requirements | The preload value shall be proposed by Supplier and agreed with HR. | Requirement | Analysis Demonstration | Not compliant | see comment to line 125
2721 | EU-MAS-D16-S_COUP-00004 | 7.2 Performance Requirements | Nominal coupling speed shall be assessed for 3 km/h. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2722 | EU-MAS-D16-S_COUP-00005 | 7.2 Performance Requirements | Maximum coupling speed shall be assessed for 5 km/h. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2723 | EU-MAS-D16-S_COUP-00006 | 7.2 Performance Requirements | Other inputs for simulation management shall be considered for: Wheel/rail Friction coefficient: 0.2 Stiffness: 1.00E+008 N/m | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2724 | HR-BP-WPD16-ML-IUC-00022 | 7.2 Performance Requirements | Simulations shall be performed considering both cases: full exceptional load MXD passengers mass according to EN15227 | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2725 | EU-MAS-D16-S_COUP-00007 | 7.2 Performance Requirements | The maximum recoverable buff stroke of the automatic coupler shall be 55 mm. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2726 | EU-MAS-D16-S_COUP-00008 | 7.2 Performance Requirements | The maximum recoverable draft stroke of the automatic coupler shall be 40 mm. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2727 | HR-BP-WPD16-ML-IUC-00025 | 7.2 Performance Requirements | The Automatic couplers shall be able to couple to an identical trainset at minimum speed of 0,8 km/h. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2728 | HR-BP-WPD16-ML-IUC-00026 | 7.2 Performance Requirements | The calculation shall be carried out taking into account that the articulation between the cars (if present) is not equipped with recoverable energy absorption elements. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2729 | HR-BP-WPD16-ML-IUC-00027 | 7.2 Performance Requirements | Calculation reports shall be delivered to HR, reporting the main characteristics of the energy absorbing sequence (e.g. force-stroke, energy-stroke, acceleration-time…). | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2730 |  | 7.2 Performance Requirements | STRUCTURAL REQUIREMENTS: Please find below the expected performance in terms of structural integrity of coupling system. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2731 |  | 7.2 Performance Requirements | AUTOMATIC COUPLER: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2732 | HR-BP-WPD16-ML-IUC-00028 | 7.2 Performance Requirements | The automatic coupler shall manage a maximum compressive load 1500kN without permanent deformation. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2733 | HR-BP-WPD16-ML-IUC-00029 | 7.2 Performance Requirements | The automatic coupler shall manage a maximum tensile load 1000 kN without permanent deformation. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2734 | EU-MAS-D16-S_COUP-00009 | 7.2 Performance Requirements | To properly allow the anticlimbers and front absorbers engagement, a shear-off system shall be provided, such that once the force required is reached, the coupler disengages and retains unimpeded into the carbody. The main dimensions of the free volume under carbody are shown with Annex TA010023678. | Requirement | Analysis Demonstration |  | Please provide mentioned annex
2735 | HR-BP-WPD16-ML-IUC-00031 | 7.2 Performance Requirements | The automatic coupler shall be characterized by a compressive shear-off load 1800 kN +/-5%. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2736 | HR-BP-WPD16-ML-IUC-00032 | 7.2 Performance Requirements | Compressive loads up to shear-off shall be carried without instability. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2737 |  | 7.2 Performance Requirements | RESCUE COUPLER: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2738 | HR-BP-WPD16-ML-IUC-00033 | 7.2 Performance Requirements | The rescue coupler shall manage a maximum compressive load 250kN without permanent deformation. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2739 | HR-BP-WPD16-ML-IUC-00034 | 7.2 Performance Requirements | The rescue coupler shall manage a maximum tensile load 300 kN without permanent deformation. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2740 | HR-BP-WPD16-ML-IUC-00035 | 7.2 Performance Requirements | The rescue coupler shall allow the rescued composition loco + train to run at speed up to 100 km/h. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2879 |  | 7 System Requirements | 7.3 Functional Requirements | Heading
2880 |  | 7.3 Functional Requirements | A detailed list of the functional requirements shall be provided during the PDR phase in the Functional Requirements Specification document. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2742 |  | 7.3 Functional Requirements | AUTOMATIC COUPLER: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2743 |  | 7.3 Functional Requirements | COUPLING & UNCOUPLING: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2744 | HR-BP-WPD16-ML-IUC-00036 | 7.3 Functional Requirements | The coupler shall allow fully automatic mechanical, pneumatic and electrical coupling and uncoupling. | Requirement | Analysis Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2745 | HR-BP-WPD16-ML-IUC-00037 | 7.3 Functional Requirements | The electrical coupling shall take place only after the mechanical coupling is accomplished. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2746 | HR-BP-WPD16-ML-IUC-00038 | 7.3 Functional Requirements | Switches for coupled signal and uncoupled signal to TCMS shall be provided. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2747 | HR-BP-WPD16-ML-IUC-00039 | 7.3 Functional Requirements | When mechanical, pneumatic and electrical coupling is complete a confirmation signal shall be generated to the vehicle control system. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2748 | HR-BP-WPD16-ML-IUC-00040 | 7.3 Functional Requirements | There shall be an indication to confirm the coupler is correctly coupled visible to persons standing in a safe position at the side of the train. | Requirement | Inspection Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2749 | HR-BP-WPD16-ML-IUC-00041 | 7.3 Functional Requirements | The automatic coupler shall be equipped with an air operated uncoupling mechanism. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2750 | HR-BP-WPD16-ML-IUC-00042 | 7.3 Functional Requirements | The coupler can be uncoupled from the driver desk through an uncoupling command. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2751 | HR-BP-WPD16-ML-IUC-00043 | 7.3 Functional Requirements | In case of pressure loss, the coupler shall be uncoupled (mechanically and electrically) manually by handle. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2752 | HR-BP-WPD16-ML-IUC-00044 | 7.3 Functional Requirements | The system shall allow the electrical head to be isolated and perform only mechanical/pneumatic coupling. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2753 | HR-BP-WPD16-ML-IUC-00045 | 7.3 Functional Requirements | The centering device shall keep the uncoupled coupler in straight position both in static and dynamic conditions of the train. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2754 | HR-BP-WPD16-ML-IUC-00046 | 7.3 Functional Requirements | Pneumatic solutions for centering device are not allowed. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2755 | HR-BP-WPD16-ML-IUC-00047 | 7.3 Functional Requirements | When activated in uncoupled condition, the self-centering device shall retain the coupler centred both horizontally and vertically within a tolerance of 0.5°. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2756 | HR-BP-WPD16-ML-IUC-00048 | 7.3 Functional Requirements | In coupled condition the centering and supporting devices shall accommodate all coupler movements. | Requirement | Analysis Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2757 | HR-BP-WPD16-ML-IUC-00049 | 7.3 Functional Requirements | It shall be possible to manually release the centering device for coupling in tight curves. The release angle of the centering device will be agreed during the detailed design phase. | Requirement | Demonstration Test | Partially Compliant | We provide a mechanical centering device with re-centering angle of +/-15°. A free adjustment is possible only at angles exceeding said +/-15°. Below this angles the centering device cannot be deactivated.
2758 | HR-BP-WPD16-ML-IUC-00050 | 7.3 Functional Requirements | In operation, wear up to the amounts that would be allowed by the maintenance instructions shall not have a negative influence on coupling integrity or control connections made through the coupler. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3127 | 33137.AA.582 | 7.3 Functional Requirements | The contractor shall provide the client with a summary of the processes and operations required for coupling, decoupling and change of direction with the time required in each case according to the template in Annex DB_Anh001_Coupling decoupling Change of direction. | Requirement | Demonstration |  | 2024-04-17 / tmdcth / Wiegand / noted
2759 |  | 7.3 Functional Requirements | COVER & ENVIROMENTAL PROTECTION: | Information
2760 | HR-BP-WPD16-ML-IUC-00051 | 7.3 Functional Requirements | The cover that protects electrical head shall operate automatically. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2761 | HR-BP-WPD16-ML-IUC-00052 | 7.3 Functional Requirements | The IP 55 degree of protection introduced by the cover shall be guarantee. | Requirement | Demonstration | Partially Compliant | Compliant for coupled condition. In uncoupled condition IP54 is achieved.
2762 | HR-BP-WPD16-ML-IUC-00053 | 7.3 Functional Requirements | A combination of seals and drains shall be used to prevent the retention of moisture and water within the electric coupler assembly. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2763 |  | 7.3 Functional Requirements | ELECTRIC HEAD: | Information
2764 | HR-BP-WPD16-ML-IUC-00054 | 7.3 Functional Requirements | The electric coupler head shall maintain positive contact under all coupler movements. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2765 | HR-BP-WPD16-ML-IUC-00055 | 7.3 Functional Requirements | The electric coupler head shall be designed for successful and reliable operation for a minimum of 10,000 cycles. Each cycle shall include advancing, coupling, uncoupling, and retracting of electric coupler head. | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2766 | HR-BP-WPD16-ML-IUC-00056 | 7.3 Functional Requirements | It shall be possible to remove electrical contacts from the face of the electric coupler for maintenance purposes. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2767 |  | 7.3 Functional Requirements | HEATING SYSTEM: | Information
2768 | HR-BP-WPD16-ML-IUC-00057 | 7.3 Functional Requirements | The heating system shall work thermostatically to allow coupling even at the lowest temperature foreseen in the operational scenarios. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2769 | HR-BP-WPD16-ML-IUC-00058 | 7.3 Functional Requirements | The heating system shall be automatically activated under a certain temperature in order to guarantee the expected functionalities of the automatic coupler. | Requirement | Demonstration | Partially Compliant | We provide according signals from thermostate to TCMS. Switching of heating lines must be provided by TCMS.
2770 | HR-BP-WPD16-ML-IUC-00059 | 7.3 Functional Requirements | It shall be possible to activate or deactivate the heating system from TCMS. | Requirement | Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand This feature must be realized at the electric supply lines onboard the vehicle.
2771 | HR-BP-WPD16-ML-IUC-00060 | 7.3 Functional Requirements | It shall be possible to switch the heating system on manually. | Requirement | Test | Partially Compliant | 2024-04-17 / tmdcth / Wiegand This feature must be realized at the electric supply lines onboard the vehicle.
2772 | HR-BP-WPD16-ML-IUC-00061 | 7.3 Functional Requirements | The heating system shall be designed in order to avoid overheating. | Requirement | Demonstration | Partially Compliant | This requires the activation of the heating elements by the TCMS (see comment toHR-BP-WPD16-ML-00058) as follows (if thermostate requires heating): uncoupled: all front face heaters on coupled: one side of front face heaters (either male or female cone side) switched off
2773 |  | 7.3 Functional Requirements | RESCUE COUPLER: | Information
2774 | HR-BP-WPD16-ML-IUC-00062 | 7.3 Functional Requirements | The rescue coupler shall allow a locomotive with standard draw hook and buffers to tow and push the train. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2775 | HR-BP-WPD16-ML-IUC-00063 | 7.3 Functional Requirements | The Rescue Coupler shall be compliant to EN 15020 §4.2.2 | Requirement | Analysis Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2218 |  |  | 8 Physical Requirements
2882 |  | 8 Physical Requirements | 8.1 Weight Requirements | Heading
2883 |  | 8.1 Weight Requirements | During the project execution the Supplier shall support the HITACHI Weight Management Process. If any specific risk or opportunity for weight increase or decrease is identified, the Supplier shall inform HITACHI about risk or opportunity and the probability of occurrence. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2884 | HR-BP-WPB05-00001 | 8.1 Weight Requirements | The Supplier shall provide the weight information for the complete system and for each item according to the BOM template [2.13]. The weight data shall include tolerances, all mountings and fixing elements, sealing, accessories, cables and whatever else necessary to the correct installation and functioning of the system/item scope of supply (i.e. oil, water etc.). | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2885 | HR-BP-WPB05-00002 | 8.1 Weight Requirements | The tolerance shall be less than 3%. Any other tolerance greater than 3% is not accepted by HITACHI. | Requirement | Analysis Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2886 | HR-BP-WPB05-00003 | 8.1 Weight Requirements | The Supplier shall provide weight data which includes for each sub-system the weight, the centre of gravity (C.o.G.) and the moment of inertia referred to the C.o.G. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
2777 |  | 8.1 Mass Requirements | AUTOMATIC COUPLER: | Information
2778 | EU-MAS-D16-S_COUP-00010 | 8.1 Mass Requirements | The weight of the complete Automatic Coupler shall be less than 400 kg. | Requirement | Test | Not compliant | Weight will be app. 430 kg
2779 |  | 8.1 Mass Requirements | RESCUE COUPLER: | Information
2780 | HR-BP-WPD16-ML-IUC-00065 | 8.1 Mass Requirements | The weight of the complete Rescue Coupler shall be less than 47 kg. | Requirement | Demonstration | Not compliant | Weight of offered rescue coupler (already delivered for Caravaggio/ROCK and HMU) is 52,3kg. The coupler is modular with no module weighing more than 25kg.
2887 |  | 8 Physical Requirements | 8.2 Mechanical interfaces & dimensions | Heading
2888 | HR-BP-WPC08-ACO-00007 | 8.2 Mechanical interfaces & dimensions | The supplier shall provide all the design documentation / drawing indicating the real dimensions, tolerances, fixing points, the required accessibility, C.o.G. of the system / equipment and/or components, in order to perform the mechanical integration of the system/equipment included in the Scope of Supply. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2889 | HR-BP-WPC08-ACO-00008 | 8.2 Mechanical interfaces & dimensions | C.o.G. coordinates shall be referred to the equipment and/or component interfaces (ex. Fixing points) with carbody. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2890 | HR-BP-WPC08-ACO-00009 | 8.2 Mechanical interfaces & dimensions | The supplier shall provide mechanical information necessary to install the system by means of: 3D model of the system subject of the specification (shall be inserted in a step file to be attached to the documentation requested in the CDRL); Documentation with all the characteristics relating to the interfaces provided on the vehicle (fixation, adjustment, etc.); Constructional tolerances affecting the system and the interfaces. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2891 | HR-BP-WPC08-ACO-00010 | 8.2 Mechanical interfaces & dimensions | All the detailed mechanical interfaces (including cabling) between the system and the vehicle will be defined and agreed between HR and the Supplier during the Design Review with no additional costs. | Requirement |  | Partially Compliant | Only if the agreed design does not required additional components with significant cost impact which were not included in the offer.
2782 |  | 8.2 Mechanical interfaces & dimensions | DIMENSIONS REQUIREMENTS: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2783 |  | 8.2 Mechanical interfaces & dimensions | AUTOMATIC COUPLER: | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2784 | EU-MAS-D16-S_COUP-00011 | 8.2 Mechanical interfaces & dimensions | Automatic coupler shall be compliant to the dimensions shown below: | Requirement | Demonstration Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2785 |  | 8.2 Mechanical interfaces & dimensions | RESCUE COUPLER: | Information
2786 | EU-MAS-D16-S_COUP-00012 | 8.2 Mechanical interfaces & dimensions | Rescue coupler shall be compliant to the dimensions shown below: | Requirement | Demonstration | Partially Compliant | 2024-04-17 / tmdcth / Wiegand The vertical misalignment is -20mm according to the sketch.
2787 |  | 8.2 Mechanical interfaces & dimensions | MECHANICAL INTEGRATION: | Information
2788 |  | 8.2 Mechanical interfaces & dimensions | AUTOMATIC COUPLER: | Information
2789 | HR-BP-WPD16-ML-IUC-00068 | 8.2 Mechanical interfaces & dimensions | The automatic coupler shall be mounted on the front side of the carbody structure. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2790 | EU-MAS-D16-S_COUP-00013 | 8.2 Mechanical interfaces & dimensions | The system shall be designed to properly interface with the structure of the carbody shown in figure below: | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3103 | EU-MAS-C08-GLY-00003 | 8.2 Mechanical interfaces & dimensions | The overall dimension of the Coupler must fit within the 3D envelope cod. TA010023678 (COUPLER ENVELOPE), including all tollerances. | Requirement | Analysis |  | Please provide mentioned TA010023678
2892 |  | 8 Physical Requirements | 8.3 Pneumatic and hydraulic interfaces | Heading
2792 | HR-BP-WPD16-ML-IUC-00070 | 8.3 Pneumatic and hydraulic interfaces | The automatic coupler shall be provided with the following pneumatic interfaces on the vehicle side: Main reservoir pipe (MRP) Brake pipe (BP) Uncoupling pipe (UP) | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2793 | HR-BP-WPD16-ML-IUC-00071 | 8.3 Pneumatic and hydraulic interfaces | The supplier shall indicate all the equipment to be foreseen on the vehicle side to guarantee the correct uncoupling function. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2794 | HR-BP-WPD16-ML-IUC-00072 | 8.3 Pneumatic and hydraulic interfaces | Type of hose connections have to be approved by HR. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
2893 | HR-BP-WPC09-00001 | 8.3 Pneumatic and hydraulic interfaces | If the system requires pneumatic supply, it shall be able to work with air having the following characteristics: The pneumatic supply normal working pressure ranges from 8 bar to 10 bar. The overpressure protection of the pneumatic supply system limits the maximum pressure at 11 bar. Such pressure level shall not lead to any fault of the equipment the air generated by the Air generation system will be compliant to the following classes according to ISO 8573-1: residual dust: class 2; residual water content: class 2; residual oil content: class 2. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2894 |  | 8 Physical Requirements | 8.4 Industrial Design | Heading
2895 | EU-MAS-C11-IDES-00001 | 8.4 Industrial Design | Any vehicle subsystem component which will be visible by passengers shall be aligned with Hitachi's Colour Scheme defined in following documents: EC100024372, External Schedule of finishing and colors EC100024373, Internal Schedule of finishing and colors | Requirement | Analysis |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
2896 |  | 8 Physical Requirements | 8.5 Materials and Processes | Heading
2897 |  | 8.5 Materials and Processes | 8.5.1 General | Heading
2898 | HR-BP-WPB13-00001 | 8.5.1 General | All plastic and/or composite material components, if present, shall be mounted in such a way as to avoid any incorrect pretension on the component itself, in its service configuration. So, special attention shall be taken to the allowed tolerances, particularly the mounting ones, and the different thermal expansion coefficients of the assembled materials. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2899 | HR-BP-WPB13-00002 | 8.5.1 General | All the parts/components subject to contact with passengers during service, to handling during transport, mounting and maintenance phases shall be devoid, as much as possible, of sharp edges and sharp corners; in case they are present, it is necessary to foresee protections, by previous HRI approval. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2900 | HR-BP-WPB13-00003 | 8.5.1 General | The supplier shall include in the design documentation: the correct designation of materials according to relevant standards; the correct identification/designation of commercial products (standard); references to internal Specification/Drawings/Procedures for others not standard parts | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2901 | HR-BP-WPB13-00004 | 8.5.1 General | If a special process will be used, the provisions defined in the AQU/IO/143 sect.00,chp.2 shall be applied. | Requirement |  | Partially Compliant | 2024-04-17 / tmdcth / Wiegand as per CbC of referenced document
2902 |  | 8.5 Materials and Processes | 8.5.2 Painting general requirements | Heading
2903 | HR-BP-WPB13-00005 | 8.5.2 Painting general requirements | The supplier shall give evidence of compliance with HR vehicle painting technical specification [2.17]. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2904 |  | 8.5 Materials and Processes | 8.5.3 Fastening system | Heading
2905 | HR-BP-WPB13-00006 | 8.5.3 Fastening system | The bolted joints shall be designed and assembled in accordance with the guidelines in the document [2.14]. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
2906 |  | 8.5 Materials and Processes | 8.5.4 Corrosion control | Heading
2907 | HR-BP-WPB13-00007 | 8.5.4 Corrosion control | For all materials, the process to prevent and control corrosion on rail vehicles shall be compliant with HR document [2.19]. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
2908 |  | 8.5 Materials and Processes | 8.5.5 Welding | Heading
2909 | HR-BP-WPB13-00008 | 8.5.5 Welding | All welded assemblies or welded connections have to be compliant with the HR technical specification document [2.23]. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2910 |  | 8.5 Materials and Processes | 8.5.6 Elastomeric parts | Heading
2911 | HR-BP-WPB13-00009 | 8.5.6 Elastomeric parts | All elastomeric parts shall meet the requirements mentioned in the document [2.24]. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
2912 |  | 8.5 Materials and Processes | 8.5.7 Bonding | Heading
2913 | HR-BP-WPB13-00010 | 8.5.7 Bonding | All Bonding shall be compliant with the requirements of the HR technical specification document [2.25]. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2914 |  | 8.5 Materials and Processes | 8.5.8 Labelling and Signage | Heading
2915 | HR-BP-WPB13-00011 | 8.5.8 Labelling and Signage | All labelling and signage shall be compliant with the requirements of the HR technical specification document [2.26]. | Requirement |  | Partially Compliant | 2023-12-18_tmdcfe: Ref. Doc [2.26] is not available, please provide. Generally, electrical parts will be labelled acc. to existing standards, e.g. as already provided in former project Caravaggio.
2219 |  |  | 9 Electrical requirements
2916 |  | 9 Electrical requirements | 9.1 Electrical components requirements | Heading
2918 | HR-BP-WPC04-00249 | 9.1 Electrical components requirements | The supplier shall be compliant with the electrical requirements reported in the attached document [2.06] and provide a detailed clause by clause. | Requirement |  | Partially Compliant | 2023-12-18_tmdcfe: As commented in Doc. Ref [2.6], EC010024455_00_CbC.xlsm
2926 |  | 9 Electrical requirements | 9.2 Electronic components requirements | Heading
2927 |  | 9 Electrical requirements | 9.3 Low Voltage Interfaces | Heading
2928 | HR-BP-WPC03-LVA-00001 | 9.3 Low Voltage Interfaces | The system shall interface with the LV system of the vehicle. | Requirement
2929 | EU-MAS-C01-VRS-00006 | 9.3 Low Voltage Interfaces | Low voltage components, according EN 50155, shall be designed in order to interface with the LV System with the following characteristics: 1. Nominal voltage (Un) [Vdc] 110.0 2. Lowest non-permanent voltage (0.6 Un) [kVdc] 66.0 3. Lowest permanent voltage (0.7 Un) [kVdc] 77.0 4. Highest permanent voltage (1.25 Un) [kVdc] 137.5 5. Highest non-permanent voltage (1.4 Un) [kVdc] 154.0 6. Class of interruption voltage supply [-] S2 7. DC ripple factor [%] 2.0 | Requirement | Analysis | Partially Compliant | 2023-12-18_tmdcfe: Electrical sensors or coupler status inticators follow power supply voltage in case of breakdown, switching or interruption of supply voltage. Thus appropriate sensor or status indicator signals transmitted to vehicle control system may interrupted accordingly.
2930 | HR-BP-WPC03-LVA-00002 | 9.3 Low Voltage Interfaces | Low voltage commands, control circuits and power devices of the systems shall be fed by train LV system (made up of train batteries and relevant battery chargers or by an external generator). | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2931 | HR-BP-WPC03-LVA-00004 | 9.3 Low Voltage Interfaces | The supplier shall provide to HR, for each separate sub-system to the LV train network, an Electrical Interface Matrix including: Voltage, current, rated power for each possible operating mode; Temporary overload; Inrush current; Load characteristics: constant power, constant resistance or constant current; | Requirement |  | Partially Compliant | 2023-12-18_tmdcfe: Data of electrical components will be documented at circuit dagrams and coupler manual accordingly.
2932 | HR-BP-WPC03-LVA-00005 | 9.3 Low Voltage Interfaces | The system power supply can be removed at any time ( in order to shut-down the equipment) without any impact or degradation on the system life. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2933 |  | 9 Electrical requirements | 9.4 Medium Voltage Interfaces | Heading
2934 | EU-MAS-C01-VRS-00005 | 9.4 Medium Voltage Interfaces | Medium voltage fixed frequency components, according EN 50533, shall be designed in order to interface with the MV System with the following characteristics: 1. Nominal voltage tri-phase line-to line (U1-L-L) [Vac] 400 (r.m.s. value) 2. Nominal Voltage mono-phase line-to-neutral (U1-L-N) [Vac] 230 (r.m.s. value) 3. Nominal frequency (F1) [Hz] 50 4. Frequency variations [-] Constant frequency 5. Frequency tolerance (%F1) [%] ± 1.0 6. Waveform output [-] Sinusoidal | Requirement | Analysis | Not Applicable | 2023-12-18_tmdcfe: No medium Voltage components or sub-systems provided by current scope of supply.
2935 |  | 9 Electrical requirements | 9.5 High Voltage Interfaces | Heading
2936 | EU-MAS-C01-VRS-00004 | 9.5 High Voltage Interfaces | High voltage components, according EN 50163, shall be designed in order to interface with the HV power supply with the following characteristics: 1. Nominal voltage (Un) [kVac] 15.00 (r.m.s. value) 2. Nominal frequency [Hz] 16+2/3 3. Lowest non-permanent voltage (Umin2) [kVac] 11.00 (r.m.s. value) 4. Lowest permanent voltage (Umin1) [kVac] 12.00 (r.m.s. value) 5. Highest permanent voltage (Umax1) [kVac] 17.25 (r.m.s. value) 6. Highest non-permanent voltage (Umax2) [kVac] 18.00 (r.m.s. value) | Requirement | Analysis | Not Applicable | 2023-12-18_tmdcfe: No High Voltage components or sub-systems provided by current scope of supply.
3084 | EU-MAS-C01-VRS-00020 | 9.5 High Voltage Interfaces | High voltage components, according EN 50163, shall be designed in order to interface with the HV power supply with the following characteristics: 1. Nominal voltage (Un) [kVac] 25.00 (r.m.s. value) 2. Nominal frequency [Hz] 50 3. Lowest non-permanent voltage (Umin2) [kVac] 17.50 (r.m.s. value) 4. Lowest permanent voltage (Umin1) [kVac] 19.00 (r.m.s. value) 5. Highest permanent voltage (Umax1) [kVac] 27.50 (r.m.s. value) 6. Highest non-permanent voltage (Umax2) [kVac] 29.00 (r.m.s. value) | Requirement | Analysis | Not Applicable | 2023-12-18_tmdcfe: No High Voltage components or sub-systems provided by current scope of supply.
2220 |  |  | 10 Functional Interfaces Requirements
2795 | HR-BP-WPD16-ML-IUC-00073 | 10 Functional Interfaces Requirements | The coupler shall provide the following interfaces to the vehicle control system: | Requirement | Demonstration
[6 empty] | Compliant | 2023-12-18_tmdcfe: as far as applicable for acc. to current scope of supply.
2937 |  | 10 Functional Interfaces Requirements | 10.1 TCMS network system interfaces | Heading
2938 | HR-BP-WPC07-00001 | 10.1 TCMS network system interfaces | The system shall be compliant with the attached specification [2.5] as for the network interface requirements and a complete CbC shall be provided. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2939 | HR-BP-WPC06-00001 | 10.1 TCMS network system interfaces | The information and signals to be exchanged on the network/bus between the System and the TCMS shall be frozen between HR and the Supplier during Design Review Phases. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2940 |  | 10 Functional Interfaces Requirements | 10.2 Digital I/O Interfaces | Heading
2941 | HR-BP-WPC01-VRS-00001 | 10.2 Digital I/O Interfaces | The number of digital I/O shall be frozen during Design Review Phases without additional costs, anyhow each control unit shall be provided at least with 20% spare digital inputs and output. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2942 |  | 10 Functional Interfaces Requirements | 10.3 Diagnostic Requirements | Heading
2943 | HR-BP-WPD27-GDG-00091 | 10.3 Diagnostic Requirements | The system shall provide over the (network/bus) interface with the TCMS, the diagnostic information required by HR during design phases in order to properly manage the system operation and its maintainability. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2944 | HR-BP-WPD27-GDG-00092 | 10.3 Diagnostic Requirements | Detailed diagnostic information shall be defined along with HR during design review phases, with no additional cost, in order to have the selective diagnostic to identify which are the faulty devices and the actions to act related to vehicle safety and train service. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2945 | HR-BP-WPD27-GDG-00093 | 10.3 Diagnostic Requirements | The Supplier shall refer to the attached specification [2.8] for the diagnostic data transmission to the TCMS and the guidelines for the filling of the System ICD Document. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2221 |  |  | 11 Condition Based Maintenance (CBM)
3104 | HR-BP-WPB21-00126 | 11 Condition Based Maintenance (CBM) | The Supplier shall provide a CbC to the CBM Generic Requirements Specification [2.9]. | Requirement |  | Not Applicable | 2024-04-17 / tmdcth / Wiegand
2222 |  |  | 12 RAMS Requirements
2946 |  | 12 RAMS Requirements | 12.1 RAM/LCC Requirements | Heading
2947 | HR-BP-WPB04-GL-00046 | 12 RAMS Requirements | The system/equipment in the Scope of Supply shall be compliant with the attached specification [2.02]. | Requirement | Analysis |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
3085 | HR-BP-WPB04-GL-00047 | 12.1 RAM/LCC Requirements | The Supplier shall be compliant with LCC targets, requirements in document [2.01], and shall provide evidence of the declared values by filling the ANNEX 1 (excel file “HR LCC Template”) of the document [2.02]. | Requirement | Analysis |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
3120 |  | 12 RAMS Requirements | 12.2 Safety Requirements for suppliers | Heading
3138 | HR-BP-WPB03-00001 | 12.2 Safety Requirements for suppliers | The system/equipment in the Scope of Supply shall be compliant with the attached specification [2.28] and a complete CbC shall be provided. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
3086 |  | 12 RAMS Requirements | 12.3 Design for Maintenance Requirements | Heading
3087 | HR-BP-WPB22-00001 | 12.3 Design for Maintenance Requirements | The system shall be compliant with document [2.29] "Design for Maintenance (DfM) Specification". A CbC of the document shall be provided. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
3106 | EU-MAS-B22-DFM-00453 | 12.3 Design for Maintenance Requirements | All Preventive maintenance tasks shall be On Condition with no task periodicity under 5 years. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
3105 | EU-MAS-B04-RAM-00005 | 12 RAMS Requirements | The system shall be compliant with document QY020024938 RAM/LCC Specification [2.01] and a complete CbC shall be provided. | Requirement |  |  | 2024-04-17 / tmdcth / Wiegand Please provide said documents
2224 |  |  | 13 Noise and Vibration Requirements
2961 | HR-BP-WPB11-00001 | 13 Noise and Vibration Requirements | The Supplier shall be responsible to design and verify that the system complies with the requirements stated in the present paragraph. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2962 |  | 13 Noise and Vibration Requirements | 13.1 Sound Insulation | Heading
2963 |  | 13 Noise and Vibration Requirements | 13.2 Noise Requirements | Heading
2964 |  | 13 Noise and Vibration Requirements | 13.3 Vibration Requirements | Heading
2688 |  |  | 14 EMC requirements
2965 |  | 14 EMC requirements | 14.1 EMC general requirements | Heading
2966 | HR-BP-WPB18-00001 | 14.1 EMC general requirements | The Supplier shall take into account his EMC classification, related to the wiring distribution in the connectors and terminals. Each category wiring shall be separated from the other categories wiring. The wires of the same category shall be grouped. | Requirement |  | Partially Compliant | 2023-12-18_tmdcfe: as far as applicable acc. to current scope of supply.
2967 | HR-BP-WPB18-00002 | 14.1 EMC general requirements | The supplier shall comply with the EMC requirements according to with the applicable standards [3.3] and [3.4]. Additional information or EMC requirements will be agreed between HRI and supplier during design reviews. | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply.
2968 | HR-BP-WPB18-00003 | 14.1 EMC general requirements | The Supplier shall provide an EMC Control Plan with details about the overall design approach, procedures and techniques to be used in order to meet the contractual EMC/EMI requirements. | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply.
2969 | HR-BP-WPB18-00004 | 14.1 EMC general requirements | The contents of the EMC Control Plan shall address, at least, the following items: EMC management (organization) EMC test plan List of deliverables Schedule of EMC activities and milestones General EMC guidelines (e.g. used methods for grounding, shielding and cable separation). | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply.
2970 |  | 14 EMC requirements | 14.2 Magnetic Field requirements | Heading
2971 |  | 14 EMC requirements | 14.3 EMC Test & reports | Heading
2972 | HR-BP-WPB18-00005 | 14.3 EMC Test & reports | In the test specifications, the test acceptance criteria and any safety margins shall be included along with a description of each test and reference to any applicable standard. | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply. No EMC Tests will be carried out and reported.
2973 | HR-BP-WPB18-00006 | 14.3 EMC Test & reports | For each of the planned tests the EMC test report will show that the test has been executed following the corresponding test procedure. Furthermore, the test report will either demonstrate that the supplied system or component fulfilled the necessary test requirements or explain why the apparatus should still be accepted despite failing to achieve the necessary acceptance criteria. These documents are equally acceptable from the apparatus supplier or a suitability experienced third party. | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply. No EMC Tests will be carried out and reported.
2974 |  | 14 EMC requirements | 14.4 EMC Certificate of Conformity | Heading
2975 | HR-BP-WPB18-00007 | 14.4 EMC Certificate of Conformity | This document shall be compliant to the European EMC Directive and shall include: • Short description of the qualified system; • Model • Manufacturer and coordinates (address + Tel…) • Application • Applicable harmonized standards • List of EMC tests performed with test standards and compliance levels • Name of the testing laboratory and accreditation levels • Name and Signature of the testing laboratory responsible EMC Engineer • Name and Signature of the Manufacturer EMC Engineer • Name and Signature of the Manufacturer president • Document numbers for EMC Test procedures and EMC Test Reports | Requirement |  | Not Applicable | 2023-12-18_tmdcfe: No electronic parts or sub-systems provided by current scope of supply. No EMC Tests will be carried out and reported.
2689 |  |  | 15 Fire and Smoke Requirements
2976 | HR-BP-WPB10-VFP-00001 | 15 Fire and Smoke Requirements | The system and all the components included in the Scope of Supply shall be compliant to the norm [3.12]. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2977 | HR-BP-WPB10-VFP-00002 | 15 Fire and Smoke Requirements | The system and all the components included in the Scope of Supply shall be compliant to attached specification [2.3]. | Requirement |  | Partially Compliant | as per CbC of referenced document
2978 | HR-BP-WPB10-NMM-00001 | 15 Fire and Smoke Requirements | The system and all the components included in the Scope of Supply shall be compliant to attached specification [2.4]. | Requirement |  | Partially Compliant | as per CbC of referenced document
2227 |  |  | 16 Eco-design requirements
2979 | HR-BP-WPB14-00029 | 16 Eco-design requirements | The system and all the components included in the Scope of Supply shall be compliant to attached specification [2.7]. | Requirement |  | Partially Compliant | as per CbC of referenced document
2228 |  |  | 17 Industrial Engineering
2980 |  | 17 Industrial Engineering | The purpose of this chapter is to define the industrial requirements which the Equipment subject of the supply shall comply with when fitted onboard of the coaches of the Train. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2981 |  | 17 Industrial Engineering | Therefore, the design of the Equipment shall implement all the necessary measures to allow the compliance with all the industrial requirements stated in this chapter. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2982 |  | 17 Industrial Engineering | 17.1 Quantitative requirements (assembly times) | Heading
2796 | EU-MAS-D16-S_COUP-00014 | 17.1 Quantitative requirements (assembly times) | Supplier shall propose the assembly time in [manhours], in order to enhance the overall performance of the coupler (cost included). | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2984 |  | 17 Industrial Engineering | 17.2 Mounting criteria | Heading
2985 | HR-BP-WPM06-00001 | 17.2 Mounting criteria | In general, during the design phase, all precaution directed to avoid mounting or installation problem shall be adopted: where an installation with a particular direction is required, it shall be well marked and visible. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2986 | HR-BP-WPM06-00002 | 17.2 Mounting criteria | In case of LRU removal and/or replacement, no working or adjustment shall be necessary on the LRU to be installed, except technical justification to be explicitly accepted by HR. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2987 | HR-BP-WPM06-00003 | 17.2 Mounting criteria | The scope of supply shall include all adjustment and mounting materials, that would be defined later in the design process with HR. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2988 | HR-BP-WPM06-00004 | 17.2 Mounting criteria | The supplier of the system to be installed shall respect, during the design phase, the general carbody tolerances and specific interfaces tolerances. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2989 |  | 17 Industrial Engineering | 17.3 Mounting Instructions and Tools | Heading
2990 | HR-BP-WPM06-00005 | 17.3 Mounting Instructions and Tools | The supplier shall provide the supplied Equipment Mounting Instructions that indicate all mounting sequences. This documentation shall be available at the First Article Inspection (FAI) of the equipment and finalized during the assembling of the first three vehicles in production. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2991 | HR-BP-WPM06-00006 | 17.3 Mounting Instructions and Tools | The supplier shall provide dedicated and/or special tools if required in the above installation instruction (including testing). | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2992 | HR-BP-WPM06-00007 | 17.3 Mounting Instructions and Tools | Those tools shall comply with applicable standards and norms (for example: CE certification, User Manuals, etc..) and codified with Part Number. This code shall be recall in the installation document and also on the special tool with a metal tag or adhesive tear. For some specific equipment a simulator function machine will be required. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2993 | HR-BP-WPM06-00008 | 17.3 Mounting Instructions and Tools | According to norms and safety regulations, each part of scope of supply heavier than 25 kg (50 lbs), shall have the interfaces for a special tool for handling, lifting and mounting. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2994 | HR-BP-WPM06-00009 | 17.3 Mounting Instructions and Tools | Mounting instructions documents shall include all indication in order to manage and mount the equipment in a safe manner during all integrations activities. In order to satisfy this point all design drawing shall be indicate at least C.o.G and lifting points. The solution shall be approved by HRI and its Industrialization department. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3088 |  | 17 Industrial Engineering | 17.4 Packaging and Handling | Heading
3089 | HR-BP-WPM06-00010 | 17.4 Packaging and Handling | Each packing study shall be shared and accepted by Industrial Engineering Hitachi Rail STS. With acceptance by the latter, it will be possible to proceed with the shipment of the material, a derogation may be granted by Industrial Engineering Hitachi Rail STS. For some systems it may be necessary to study a packaging that interfaces with the assembly equipment, therefore the supplier is called upon to collaborate to find a solution that satisfies this requirement. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
3090 | HR-BP-WPM06-00011 | 17.4 Packaging and Handling | Each material shall be recognizable with a special tear-resistant adhesive plate, reporting the code, revision and date of manufacture, in the case of energy accumulators, the date of first charge and the date by which it shall be put into service are also required. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
3091 | HR-BP-WPM06-00012 | 17.4 Packaging and Handling | On the basis of the E-BOM and M_BOM, Industrial Engineering will issue the RDAs which will follow a packaging logic according to the assembly cycle set up on the production lines in HR STS, therefore the supplier will have to satisfy the requests of Industrial Engineering instead of a number of kits and dedicated packaging. | Requirement | Analysis
3092 | HR-BP-WPM06-00013 | 17.4 Packaging and Handling | Industrial Engineering requires the supplier to study the logic of returnable packaging. | Requirement | Analysis | Compliant | 2024-04-17 / tmdcth / Wiegand
3074 |  |  | 18 Quality Requirements
3093 | HR-BP-WPM08-00001 | 18 Quality Requirements | The supplier shall fulfil the Quality Assurance General requirements stated in the HR document AQU/IO/143 (rev. 10 of 18/10/2017, or further issue at the date of the P.O.) and HR's Quality Plan. | Requirement |  | Partially Compliant | as per CbC of referenced document
3094 | HR-BP-WPM08-00002 | 18 Quality Requirements | The system provider shall comply at least to ISO 9001:2015. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3095 | HR-BP-WPM08-00003 | 18 Quality Requirements | All special processes shall be qualified according to AQU/IO/143 and HR's Quality Plan. | Requirement |  | Partially Compliant | as per CbC of referenced document
3096 | HR-BP-WPM08-00004 | 18 Quality Requirements | All suppliers shall prepare a production plan based on the GANTT diagram with the indication of the activities program and the planning of the resources. The production plan shall be available during the FAI activity and it shall be present on the quality assurance plan. | Requirement
3097 | HR-BP-WPM08-00005 | 18 Quality Requirements | The product shall have a nameplate with the following data: Supplier name; Production Date; Part number code; Revision number; Serial number; Target data. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3098 | HR-BP-WPM08-00006 | 18 Quality Requirements | With reference to document AQU/IO/143 section 01 chapter 1, the scope of supply shall belong to the applicable “Classification Table” with the specified “Critical Level”. | Requirement |  | Partially Compliant | as per CbC of referenced document
3101 | HR-BP-WPM08-00007 | 18 Quality Requirements | The supplier shall provide a Quality Plan shall according to UNI ISO 10005:2018 standard. | Requirement
3102 | HR-BP-WPM08-00008 | 18 Quality Requirements | The supplier Quality Plan (and/or other Quality documents according to the above mentioned classification) shall be submitted to HRI, through the Supplier Portal, within thirty (30) calendar days as of the date of receipt of the HRI Order and, however, before the start of the work. | Requirement
3108 | HR-BP-WPD16-ML-IUC-IUC-00102 | 18 Quality requirements | The applicable "Critical Level" shall be 2. | Requirement
2229 |  |  | 19 Software Quality Assurance
2690 | HR-BP-WPB19-00001 | 19 Software Quality Assurance | Each software suppliers shall fill and return to Hitachi a dedicated file called Software Requirements and Deliverables file [2.21] with the information needed to make the Contractor able to perform the required software quality and safety assurance activities. Detailed requirements about the required information are contained in dedicated requirements in the same SRDM file. | Requirement | Analysis | Not Applicable | no software in scope of supply
2230 |  |  | 20 Cyber Security Assurance
2995 | HR-BP-WPB20-00001 | 20 Cyber Security Assurance | Each software suppliers shall fill and return to Hitachi a dedicated file called Software Requirements and Deliverables file [2.11] with the information needed to make the Contractor able to perform the required software quality and safety assurance activities. Detailed requirements about the required information are contained in dedicated requirements in the same SRDM file. | Requirement |  | Not Applicable | no software in scope of supply
2231 |  |  | 21 Test and validation requirements
2998 |  | 21 Test and validation requirements | 21.1 Component / System Design Qualification Tests | Heading
2999 |  | 21.1 Component / System Design Qualification Tests | 21.1.1 Type testing Activities | Heading
3000 | HR-SyRS-TMP-00069 | 21.1.1 Type testing Activities | The Supplier shall realize all type tests in its workshops or external laboratory with the witness of HR and Final Customer. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3001 | HR-SyRS-TMP-00070 | 21.1.1 Type testing Activities | The Supplier shall provide to HR the original copies of the test reports. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3002 | HR-SyRS-TMP-00101 | 21.1.1 Type testing Activities | A system communication integration test is expected at Hitachi facilities before the installation on the vehicle. During design phase Hitachi and the supplier shall define the equipment and the support necessary to carry out this activity. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3003 | HR-SyRS-TMP-00071 | 21.1.1 Type testing Activities | The type tests shall be carried out in the following cases: New product; In case of change of the production site; In case of design modifications of the product; In case of significant changes in the production process. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3004 |  | 21.1.1 Type testing Activities | In case the supplier provides an equipment/system already qualified it shall be agreed with HR if this qualification can be used to demonstrate the system compliance. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3005 |  | 21.1.1 Type testing Activities | In case of existing type tests reports (for example related to fire and smoke behaviour) they have not to be prior to 5 years. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3006 | HR-SyRS-TMP-00072 | 21.1.1 Type testing Activities | The Supplier shall agree with HR the testing program and invite HR technicians to witness the tests with a certain anticipation (minimum 15 days before the test execution). | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3048 | HR-BP-WPD16-ML-IUC-00075 | 21.1.1 Type testing Activities | Tests shall be conducted to demonstrate the functionalities required by this System Requirement Specification. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3049 | HR-BP-WPD16-ML-IUC-00076 | 21.1.1 Type testing Activities | The Supplier shall realize all type tests in its workshops or external laboratory with the witness of HR and Final Customer. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3050 | HR-BP-WPD16-ML-IUC-00077 | 21.1.1 Type testing Activities | The Supplier shall provide to HR the original copies of the test reports. | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3051 | HR-BP-WPD16-ML-IUC-00078 | 21.1.1 Type testing Activities | Every single test required by TSI LOC&PASS or TSI PRM shall be conducted in accredited laboratories (ISO17025). | Requirement | Demonstration | Compliant | 2024-04-17 / tmdcth / Wiegand
3052 |  | 21.1.1 Type testing Activities | AUTOMATIC COUPLER: | Information
3053 | HR-BP-WPD16-ML-IUC-00079 | 21.1.1 Type testing Activities | Automatic Coupler shall be tested for structural strength in buff. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3054 | HR-BP-WPD16-ML-IUC-00080 | 21.1.1 Type testing Activities | Automatic Coupler shall be tested for structural strength in draft. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3055 | HR-BP-WPD16-ML-IUC-00081 | 21.1.1 Type testing Activities | Tests shall be conducted to confirm the ability of the coupler to remain properly centered. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3056 | HR-BP-WPD16-ML-IUC-00082 | 21.1.1 Type testing Activities | Tests shall be conducted to confirm the gathering range. | Requirement | Test | Partially Compliant | Specific gathering range test for this project/product is not considered. We refer to existing gathering range validation unless otherwise agreed.
3057 | HR-BP-WPD16-ML-IUC-00083 | 21.1.1 Type testing Activities | Tests shall be made to confirm the proper functionality of the coupler release system. | Requirement | Test | Partially Compliant | We refer to existing validation of identical system
3058 | HR-BP-WPD16-ML-IUC-00084 | 21.1.1 Type testing Activities | Tests shall be made to ensure that a watertight seal is maintained under all conditions. | Requirement | Test | Partially Compliant | Specific watertightness test for this project/product is not considered. We refer to existing validation unless otherwise agreed.
3059 | HR-BP-WPD16-ML-IUC-00085 | 21.1.1 Type testing Activities | The equipment supplier shall provide evidence of a successful life cycle test, demonstrating 10,000 cycles for the same electrical head design including advancing, coupling, uncoupling, and retracting of electrical heads. Alternate methods to demonstrate life cycle requirements may be proposed for approval. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3060 | HR-BP-WPD16-ML-IUC-00086 | 21.1.1 Type testing Activities | The retracting mechanism shall be disassembled after the 10,000 cycles test to verify and record equipment condition and wear. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3061 | HR-BP-WPD16-ML-IUC-00087 | 21.1.1 Type testing Activities | There shall be no deformations, cracks, crack indications, signs of material fatigue, or evidence of overstress after 10,000 cycles test. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3062 | HR-BP-WPD16-ML-IUC-00088 | 21.1.1 Type testing Activities | Test shall be made to verify the possibility of electrical head insulation. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3063 | HR-BP-WPD16-ML-IUC-00089 | 21.1.1 Type testing Activities | Test shall be made to verify the possibility of manual uncoupling. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3064 | HR-BP-WPD16-ML-IUC-00090 | 21.1.1 Type testing Activities | Tests shall be conducted to prove that the system respect the requested measures and tolerances. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3065 | HR-BP-WPD16-ML-IUC-00091 | 21.1.1 Type testing Activities | Tests shall be conducted to verify that the system is able to perform the movements requested. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3066 | HR-BP-WPD16-ML-IUC-00092 | 21.1.1 Type testing Activities | Tests shall be conducted to measure the final weight of the system. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3067 | HR-BP-WPD16-ML-IUC-00093 | 21.1.1 Type testing Activities | Tests shall be conducted to verify the seamlessness of electric signals as well as that of the air supply for two coupled couplers | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3068 | EU-MAS-D16-S_COUP-00015 | 21.1.1 Type testing Activities | Test (or any other verification procedure to be approved by HR) shall be conducted to verify that the coupling system (both automatic coupler and semi-permanent coupler) is able to handle the requested 5 km/h coupling velocity of vehicles. | Requirement | Analysis | Partially Compliant | Validation will be provided by impact simulation
3069 | HR-BP-WPD16-ML-IUC-00095 | 21.1.1 Type testing Activities | Any further type tests shall be performed in order to comply with all those required by EN16019 §5.1 | Requirement | Test | Partially Compliant | The position of the strain gauges in Schaku-tests may deviate from the examples given in section 5.
3070 |  | 21.1.1 Type testing Activities | RESCUE COUPLER: | Information
3071 | HR-BP-WPD16-ML-IUC-00096 | 21.1.1 Type testing Activities | Tests shall be performed in compliance with EN15020 §5.1.2 for rescue coupler (static loads). | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3072 | HR-BP-WPD16-ML-IUC-00097 | 21.1.1 Type testing Activities | Tests shall be performed in compliance with EN15020 §5.1.3 for rescue coupler (coupling/uncoupling). | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3007 |  | 21.1 Component / System Design Qualification Tests | 21.1.2 Type Testing documentation | Heading
3008 | HR-SyRS-TMP-00073 | 21.1.2 Type Testing documentation | The Supplier shall submit for HR approval a System Validation Program, which shall include all of the V&V Activities and type tests. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3009 | HR-SyRS-TMP-00074 | 21.1.2 Type Testing documentation | The Supplier shall submit for HR approval test specification and test procedures, according to the CDRL documentation. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3010 |  | 21.1 Component / System Design Qualification Tests | 21.1.3 Type testing requirements | Heading
3011 |  | 21 Test and validation requirements | 21.2 Component / System Routine Tests | Heading
3012 | HR-SyRS-TMP-00075 | 21.2 Component / System Routine Tests | The series test procedures shall be provided by the supplier for HR agreement at least 1 month before the beginning of the testing activity. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3013 | HR-SyRS-TMP-00076 | 21.2 Component / System Routine Tests | Series test of the stand-alone system/equipment shall be performed by the supplier in his facilities. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2798 | HR-BP-WPD16-ML-IUC-00098 | 21.2 System Routine Tests | All tests prescribed by EN16019 §5.2 - Routine Tests shall be performed for automatic coupler. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2799 | HR-BP-WPD16-ML-IUC-00099 | 21.2 System Routine Tests | All tests prescribed by EN15020 §5.2 - Routine Tests shall be performed for rescue coupler. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
3014 |  | 21 Test and validation requirements | 21.3 Vehicle Design Qualification Tests | Heading
2801 | HR-BP-WPD16-ML-IUC-00100 | 21.3 Vehicle Level Test | Functional integration & performance tests shall be performed at train level in order to ensure the expected functionalities & performances of gangway system after assembly with carbody. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2802 | HR-BP-WPD16-ML-IUC-00101 | 21.3 Vehicle Level Test | Vehicle level tests shall be conducted in HR Pistoia, with the attendance of Supplier. | Requirement | Test | Compliant | 2024-04-17 / tmdcth / Wiegand
2996 |  | 21 Test and validation requirements | The Supplier shall be responsible to perform all type tests required to qualify and demonstrate the compliance of the system to Hitachi and Customer requirements taking into account the given environmental conditions and the acceptance criteria. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
2997 |  | 21 Test and validation requirements | The following different levels of type tests shall be foreseen to qualify the system: Component / System Design Qualification Tests (stand-alone) Vehicle Design Qualification Tests (vehicle integration) | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3015 |  | 21.3 Vehicle Design Qualification Tests | 21.3.1 Vehicle type tests | Heading
3016 |  | 21.3.1 Vehicle type tests | 21.3.1.1 Integration tests on Vehicle | Heading
3017 |  | 21.3.1.1 Integration tests on Vehicle | Integration tests of the systems on vehicle will be carried out by HR in order to verify the correct functionality and performance of the system installed on the train and, moreover, its interfaces and compatibility with other equipment of the train. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3018 |  | 21.3.1.1 Integration tests on Vehicle | Functional and communication tests are expected to be executed in addition to specific performance and integration test, according to the test plan. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3019 | HR-SyRS-TMP-00077 | 21.3.1.1 Integration tests on Vehicle | The Supplier shall provide all the necessary technical assistance (tools, people, etc.) to HR in order to perform those tests until they will be successfully executed. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3020 |  | 21.3.1 Vehicle type tests | 21.3.1.2 Performance test on Vehicle | Heading
3021 |  | 21.3.1.2 Performance test on Vehicle | These tests will be done by HR in order to verify correct functioning of the system on the vehicle. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3022 |  | 21.3.1.2 Performance test on Vehicle | The tests will be done according EN 50215 [3.18]. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3023 |  | 21.3.1.2 Performance test on Vehicle | Technical assistance from the Supplier shall be given to allow HR to perform these tests autonomously. | Information |  |  | 2024-04-17 / tmdcth / Wiegand / noted
3024 |  | 21.3 Vehicle Design Qualification Tests | 21.3.2 Vehicle routine tests | Heading
3025 | HR-SyRS-TMP-00078 | 21.3.2 Vehicle routine tests | The supplier shall support HR during the series test of the system/equipment on the first train. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2232 |  |  | 22 Homologation requirements
2233 |  |  | 23 Documentation requirements
3026 |  | 23 Documentation requirements | 23.1 Format definition | Heading
3027 | HR-SyRS-TMP-00079 | 23.1 Format definition | The following formats and supports shall be used for the documentation: | Requirement |  | Partially Compliant | see below
Drawings in parts catalogue and user manual would be TIFF by default. As a vector format Voith could offer AI (Adobe Illustrator). Any format beyond the standard would need to be charged.
3028 | HR-SyRS-TMP-00080 | 23.1 Format definition | Each drawing or technical document shall at least contain the indication listed as follows: Name of company; Title; Identification codes (work order, project, P/N) Revision index; Table or page number; Verification and approval signatures. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3029 |  | 23 Documentation requirements | 23.2 Drawings requirements | Heading
3030 | HR-SyRS-TMP-00081 | 23.2 Drawings requirements | The structure of the drawings shall be in accordance to the following table: | Requirement |  | Partially Compliant | We provide only main drawing of complete product to customer, no detail drawings
3031 | HR-BP-WPC08-VMM-00013 | 23.2 Drawings requirements | Drawings shall be provided in compliance with ISO 5457 [3.28], UNI EN ISO 10209 [3.29], UNI EN ISO 5456 [3.30]. | Requirement
3032 |  | 23 Documentation requirements | 23.3 Language | Heading
3033 | HR-BP-WPM03-00001 | 23.3 Language | All the documentation included in the Scope of Supply shall be provided in English Language. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3034 |  | 23 Documentation requirements | 23.4 Project documentation | Heading
3035 | HR-BP-WPM03-00002 | 23.4 Project documentation | The supplier shall provide all the applicable CDRL documents as reported in the document [2.22]. | Requirement |  | Partially Compliant | CDRL list to be mutually agreed
3036 | HR-BP-WPM03-00003 | 23.4 Project documentation | The supplier shall provide at least the following documents, as applicable: System Technical description; Performance calculations (as required and applicable); Responses and information to the project specific request (listed for each section/system); Detailed BoM (according to the BoM template) including the weight data of each component and the related drawing number and revision; Interface doc (functional interface) and drawings (mechanical/electrical); Functional descriptions; Diagnostic documents; Electrical schemes; Power consumptions of all subsystem in all possible operative modes and including inrush currents of power equipment; List of special tools and related description; List of PTU and BTE and related descriptions; Spare parts list; RAMS documentation; Preventive maintenance: The preventive maintenance plan of the system / equipment shall be described indicating the intervals and average time required and the mileage between the minor and major overhauls; Required Alternatives: In this file the "alternative solutions" that the specifications require in the relevant section shall be described, illustrating advantages and disadvantages and impact on the functions and characteristics of the vehicle required in the technical specifications; Proposed Alternative Solutions Requiring a Specification Change: In this file "alternative solutions" proposed by the supplier and not provided in the technical specification shall be described. This solution may not be fully compliant with the technical specification. The supplier shall describe the advantages and disadvantages of such solutions, as well as describe the changes necessary for the proposal to become compliant with the technical specifications. Test plan; Test specifications and procedures, including the acceptance criteria; Test reports; Manuals and trainings documentation. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
2235 |  |  | 24 Manuals and Trainings Requirements
3073 | HR-BP-WPM11-00001 | 24 Manuals and Trainings Requirements | The Supplier shall provide manuals and training documentation in accordance with the attached specification [2.10]. | Requirement |  | Partially Compliant | Compliance unknown, as the attachment is missing.
2234 |  |  | 25 Special Tools, PTU, BTE requirements
3037 | HR-SyRS-TMP-00087 | 25 Special Tools, PTU, BTE requirements | The Supplier shall define the list of the Special Tools and test equipment in accordance with the Section 08 of the AQU IO 143 and the contractual conditions. | Requirement |  | Partially Compliant | as per CbC of referenced document
3038 | HR-SyRS-TMP-00088 | 25 Special Tools, PTU, BTE requirements | The Supplier shall define and agree with HR the list of the Special Tools, PTUs and BTEs that are required for the equipment installation, the monitor and check of the equipment functionality (control and off-line diagnostic), the equipment 1st and 2nd level maintenance, repair and troubleshooting in accordance with the requirements stated in this SyRS. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3039 | HR-SyRS-TMP-00089 | 25 Special Tools, PTU, BTE requirements | In case the PTU is composed by a laptop or a standard personal computer, both the relative SW application and the eventual non-standard wiring to interface the PC and the system supplied, shall be included in the Scope of Supply. | Requirement |  | Not Applicable | no software in scope of supply
3040 | HR-SyRS-TMP-00090 | 25 Special Tools, PTU, BTE requirements | The application software (PTU) to be installed on the laptop to assure the interface and the communication between the laptop itself and the system shall be with no license limitation. | Requirement |  | Not Applicable | no software in scope of supply
3041 | HR-SyRS-TMP-00091 | 25 Special Tools, PTU, BTE requirements | The application software (PTU) shall have several security levels to limit the access and the control of the system (i.e. level crew, technicians, programmer…). | Requirement |  | Not Applicable | no software in scope of supply
2236 |  |  | 26 Requirements Management and Traceability
3042 | HR-BP-WPM02-00001 | 26 Requirements Management and Traceability | During all the project's lifecycle the Supplier shall support the HR Requirement Management Process in order to perform verification and validation activities. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3043 | HR-BP-WPM02-00002 | 26 Requirements Management and Traceability | The supplier shall fill in the cells of the End Customer Compliance Matrix spreadsheet [2.15] portion extracted by the vehicle compliance matrix where all the TS requirements have been included. | Requirement |  |  | please provide example sheet of said document
3044 | HR-BP-WPM02-00003 | 26 Requirements Management and Traceability | The supplier shall fill in the cells of the SyRS Compliance Matrix spreadsheet [2.16], generated from present document, for all the requirements included in this specification. | Requirement |  |  | please provide example sheet of said document
3045 | HR-BP-WPM02-00004 | 26 Requirements Management and Traceability | For each requirement the supplier shall indicate statement of compliance status (“Compliance” column) between following value: Compliant (C) Not Compliant (NC) Not Applicable (NA) Only in case of “Not Compliant” or “Not Applicable” compliance status, the Supplier shall define a justification (“Compliance Argument” column) in order to explain the reason why the fully compliance is not going to be guaranteed. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
3046 | HR-BP-WPM02-00005 | 26 Requirements Management and Traceability | For each applicable and compliant requirement, the Supplier shall indicate: the Satisfying Document which will be submitted (in which the requirement has been addressed or satisfied) that supports the requirement's verification process; the Validation Method; the Validation Document that supports the requirement’s validation process. | Requirement |  | Compliant | 2024-04-17 / tmdcth / Wiegand
Click for pictures sizing&fixing

## Parameter (hidden)
Validation Method | Req. Type | Allocation areas | Object Type | RBS | WP Owner | Title | WPList
Inspection | Functional | Vehicle System Requirements | Heading | --Vehicle Performances & Trasversal-- |  | 1. Introduction | WP A1_Standards and Technical Admission Requirement
Analysis | Operational | Vehicle Operability Mode | Requirement | Climatic Confort |  | 1.1 System Scope | WP A2_Requirements from ITT
Demonstration | Performance | Climatic Confort | Information | Product Safety |  | 1.2 Definitions | WP A3_Requirements from Tender Documents
Test | Quality | Product Safety |  | RAM - LCC |  | 1.3 Acronyms and abbreviations | WP A4_Infrastructure Requirements
C.o.C. | Standard | RAM - LCC |  | Weight Requirements |  | 2. Reference standard and documents | WP A5_Benchmarking
| Dynamic Performance | Weight Requirements | Acceptance | Infrastructure Requirements |  | 2.1 Customer documents | WP B1_Vehicle Performances
| Documentation | Infrastructure Requirements | Accepted | Kinematics relative movements |  | 2.2 Railworthiness standard | WP B2_Climatic Conditions
| Interface | Kinematics relative movements | Accepted With Comment | Design Limit Line and Kinematic Envelope |  | 2.3 Other contractual Standards and documents | WP B3_Project Safety
|  | Design Limit Line and Kinematic Envelope | Rejected | Vehicle Running Dynamics |  | 2.4 HRI Internal documents | WP B4_RAM/LCC
ComplianceLevel | RFC Status | Vehicle Running Dynamics |  | Fire Safety |  | 2.5 Reference Documents | WP B5_Weight Performance
Compliant | Open | Fire Safety |  | Noise and Vibration |  | 3. Train characteristics and parameters | WP B6_Infrastructure Analysis
Not compliant | Approval | Noise and Vibration | Classification | Aerodynamics |  | 3.1 Train Characteristics | WP B7_Design Limit Line and Kinematic Envelope
Partially Compliant | Rejected | Aerodynamics | Mandatory | Materials and Technologies - LCA |  | 3.2 Vehicle Capacity | WP B8_Kinematics and Relative Movements
Not Applicable |  | Materials and Technologies - LCA | Critical | Design For Environment |  | 4. Operational Scenario | WP B9_Bogie Movements
|  | Design For Environment | Standard | Passive Safety |  | 4. 1Environmental conditions | WP B10_Running Dynamics
RFC_Type | Bool | Passive Safety |  | EMC |  | 4.2 Structural Strength and Fatigue | WP B11_Fire Safety
Clarification | True | EMC |  | General Software |  | 5. SYSTEM REQUIREMENTS | WP B12_Noise and Vibration
Change | False | General Software |  | Cyber Security |  | 5.1 General System Requirements | WP B13_Thermal Insulation
Deletion |  | Cyber Security |  | Diagnostics |  | 5.2 System Architecture | WP B14_Internal Airflow
| Test Category | Diagnostics |  | CBM |  | 5.3 Main Components | WP B15_Aerodynamics
| Train Series Test | CBM |  | --General Architecture/Integration-- |  | 5.4 System Performance Requirements | WP B16_Pressure Protection
Acceptance | Train Type Test | High Voltage Architecture |  | Vehicle System Requirements |  | 5.5 Normal mode Performance Requirements | WP B17_Materials and Technology
Accepted | Car Level Test | Medium Voltage Architecture |  | Vehicle Operability Mode |  | 5.6 Degraded mode Performance Requirements | WP B18_Design for Environment
Rejected | Combined Test | Low Voltage Architecture |  | High Voltage Architecture |  | 6. Functional Requirements | WP B19_Carbody Structural Calculation
Shared | Subsystem Test | Vehicle Earting Requirements |  | Medium Voltage Architecture |  | 7. Physical Requirements | WP B20_Bogie Structural Calculation
| Component Test | Electronic Circuits |  | Low Voltage Architecture |  | 7.1 Mechanical Requirements | WP B21_Passive Safety
|  | General Electrical Requirements |  | Vehicle Earting Requirements |  | 7.2 Dimensions | WP B22_EMC
|  | Vehicle Layout |  | Electronic Circuits |  | 7.3 Mechanical interfaces | WP B23_Software V&V
|  | Vehicle Barrier Free Design |  | General Electrical Requirements |  | 7.4 Pneumatic and hydraulic interface | WP B24_Cyber Security
|  | Vehicle Assembly Concept |  | Vehicle Layout |  | 7.5 Weight Requirements | WP B25_Condition Based Maintenance (CBM)
|  | Vehicle Laying all Media |  | Vehicle Barrier Free Design |  | 7.6 Maintainability and Interchangeability Requirements | WP C1_Vehicle Operability
|  | Network Architecture |  | Vehicle Assembly Concept |  | 7.7 Water tightness / IP protection | WP C2_Vehicle Functions
|  | Car Body |  | Vehicle Laying all Media |  | 8. System electrical interfaces and electric components | WP C3_Traction System Architecture
|  | Vehicle Extirior Front-End |  | Network Architecture |  | 8.1 Electrical Interfaces Requirements | WP C4_HV Electrical Architecture
|  | Windows and Windscreen |  | --Systems and Components-- |  | 8.2 High Voltage Interfaces | WP C5_MV-LV Electrical Architecture
|  | Floor |  | All Systems |  | 8.3 Medium Voltage Interfaces | WP C6_Earthing
|  | Acoustic and Thermal insulation |  | All Software |  | 8.4 Low Voltage Interfaces | WP C7_Electrical Schematics and Cabling
|  | Interiors Design |  | Car Body |  | 8.5 Grounding requirements | WP C8_Electrical Equipment and Cabinets
|  | Driver's Cabin |  | Vehicle Extirior Front-End |  | 8.6 Network Interface Requirements | WP C9_Train Control Architecture
|  | HVAC Cab System |  | Windows and Windscreen |  | 8.7 Electro-mechanical components Requirements | WP C10_Networking Architecture
|  | Seats |  | Floor |  | 8.8 Electronic components Requirements | WP C11_Vehicle Layout
|  | Toilets |  | Acoustic and Thermal insulation |  | 9. Functional Interfaces Requirements | WP C12_Vehicle and Components Assembly
|  | Catering |  | Interiors Design |  | 9.1 TCMS and Control system Interfaces | WP C13_Laying of all Media
|  | Doors System |  | Driver's Cabin |  | 9.2 Digital/Analog I/O and signal Interfaces | WP C14_Labels and Signs
|  | Lift |  | HVAC Cab System |  | 10. Diagnostic Requirements | WP C15_Industrial Design
|  | Industrial Design |  | Seats |  | 11. Software Requirements | WP C16_Barrier Free Design (PRM)
|  | Label and Signs |  | Toilets |  | 12. RAMS Requirements | WP C17_Vehicle Master Model & LBS
|  | Bogie and Running Gear |  | Catering |  | 13. Acoustic Noise Requirements | WP D1_Carbody and Interfaces
|  | Wheel Lubricator |  | Doors System |  | 14. Shock and Vibration requirements | WP D2_Lifting and Re-railing Concept
|  | Propulsion System |  | Lift |  | 15. EMC requirements | WP D3_Vehicle Exterior Front End
|  | Energy Power Collection |  | Industrial Design |  | 16. Material and Painting | WP D4_Driver's Cabin
|  | Energy Meter |  | Label and Signs |  | 16.1 Fire and Smoke Requirements | WP D5_Cab Radio System
|  | Brake Resistor |  | Bogie and Running Gear |  | 16.2 Eco-design | WP D6_HVAC Unit
|  | Auxiliary Power Supply |  | Wheel Lubricator |  | 16.3 Painting General Requirements | WP D7_External Doors
|  | Battery |  | Propulsion System |  | 17. Quality Requirements | WP D8_Braking & Air Supply
|  | Battery charger |  | Energy Power Collection |  | 17.1 Classification Table and critical level | WP D9_Fire Protection
|  | Traction Motor |  | Energy Meter |  | 17.2 Quality Plan | WP D10_Lighting
|  | Diesel Power Pack |  | Brake Resistor |  | 18. Industrial Engineering requirements | WP D11_Toilet
|  | TACU |  | Auxiliary Power Supply |  | 19. Mock-up and prototypes | WP D12_Signalling
|  | ObESS |  | Battery |  | 20. Special Tools requirements | WP D13_Interiors
|  | Sanding System |  | Battery charger |  | 21. Tests and design validation | WP D14_Floor Systems
|  | Pneumatic System |  | Traction Motor |  | 21.1 Design review | WP D15_Windows and Windshield
|  | Brake System |  | Diesel Power Pack |  | 21.2 Type test | WP D16_Inter-Unit Connections
|  | Inter-Unit Connections |  | TACU |  | 22. Homologation requirements | WP D17_Inter-Car Connections
|  | Inter-Car Connections |  | Power Battery |  | 23. Manuals and Training Requirements | WP D18_Gangway
|  | Gangway |  | Sanding System |  | 24. Documentation Requirements | WP D19_Bogie
|  | Fire Protection System |  | Pneumatic System |  | 24.1 Contractual Deliverables Requirements List (CDRL) | WP D20_Energy Measuring
|  | HVAC Compartment System |  | Brake System |  | 24.2 Delivery dates | WP D21_Energy Power Collection
|  | Lighting |  | Inter-Unit Connections |  | 24.3 Change management | WP D22_Propulsion System
|  | Conventional Train Circuit |  | Inter-Car Connections |  | 24.4 Language and format of Documentation | WP D23_Traction Motor
|  | Signalling |  | Gangway |  | 24.5 Drawings | WP D24_Braking Resistor
|  | Cab Radio System |  | Fire Protection System |  | 25. System Requirements Compliance and Traceability | WP D25_Traction and Auxiliary Control System
|  | Dead-man |  | HVAC Compartment System |  | 26. Industrial Design | WP D26_Auxiliary Power Supply
|  | Event Recorder |  | Lighting |  |  | WP D27_Battery Charger
|  | TCS |  | Conventional Train Circuit |  |  | WP D28_Battery
|  | MDS |  | Signalling |  |  | WP D29_Diesel Power Pack
|  | Telediagnostics |  | Cab Radio System |  |  | WP D30_Train Control System
|  | Communication and Infotainment |  | Dead-man |  |  | WP D31_Diagnostics and Telediagnostics
|  | Obstacle Detection |  | Event Recorder |  |  | WP D32_Event Recorder
|  | Miscellaneous |  | TCS |  |  | WP D33_Communication and Infotainment
|  |  |  | MDS |  |  | WP D34_Electronic Circuits
|  |  |  | Telediagnostics |  |  | WP D35_Obstacle Detection
|  |  |  | Communication and Infotainment |  |  | WP D36_Miscellanous
|  |  |  | Obstacle Detection |  |  | WP D37_Power Battery
|  |  |  | Miscellaneous |  |  | WP D38_Cab Simulator
WP E1_Structural Tests
WP E2_Climatic Chamber
WP E3_Aerodynamic Tests
WP E4_Runnings Dynamic Tests
WP E5_EMC Tests
WP E6_Noise and Vibration Tests
WP E7_Project Validation
WP M1_Project Engineering
WP M2_Planning Engineering
WP M3_Requirements Management
WP M4_Document Management and Data Exchange
WP M5_Coverage and Risk analysis
WP M6_Certification Management
WP M7_IPR Analysis
WP M8_Project Management
WP M9_Manufacturing
WP M10_Supply Chain
WP M11_Quality
WP M12_Service and Warranty
WP M13_Manuals and Training

## SRD to Workpackage Map (hidden)
Taken from Issue 25 of Sergio's Spreadsheet | Master Spreadsheet Issue 25
SRD Title | WP allocation | Row Labels
SRD_01 - Air & Brake System | WP D08_Braking / Air Supply | WP D01_Carbody and interfaces
SRD_02 - Cab Coupler System | WP D16_Inter-Vehicle Connections | SRD_42 - Carbody Shell
SRD_03 - Inter-Car Coupler System | WP D17_Inter-Car Connections | WP D03_Vehicle Exterior Front End
SRD_04 - Inter-car Gangway System | WP D18_Gangway | SRD_23 - Vehicle Front End
SRD_05 - Saloon HVAC | WP D06_HVAC Unit | WP D04_Drivers Cabin
SRD_06 - Cab HVAC | WP D06_HVAC Unit | SRD_22 - Driver's Desk
SRD_07 - Ducting System | WP D06_HVAC Unit | WP D05_Cab Radio System
SRD_08 - Exterior Door | WP D07_External Doors | SRD_13 - Radio GSMR
SRD_09 - Sliding Step | WP D07_External Doors | WP D06_HVAC Unit
SRD_10 - Fire Protection System | WP D09_Fire Protection System | SRD_05 - Saloon HVAC
SRD_11 - PIS | WP D33_Communication and infotainment | SRD_06 - Cab HVAC
SRD_12 - APC (Automatic Passenger Counting) System | WP D33_Communication and infotainment | SRD_07 - Ducting System
SRD_13 - Radio GSMR | WP D05_Cab Radio System | WP D07_External Doors
SRD_14 - Signalling System | WP D12_Signalling | SRD_08 - Exterior Door
SRD_15 - Interiors Equipment | WP D13_Interiors | SRD_09 - Sliding Step
SRD_16 - Toilet & Water System | WP D11_Toilet | WP D08_Braking / Air Supply
SRD_17 - CCTV System | WP D33_Communication and infotainment | SRD_01 - Air & Brake System
SRD_18 - Saloon Lighting | WP D10_Lighting | WP D09_Fire Protection System
SRD_19 - Exterior Lighting | WP D10_Lighting | SRD_10 - Fire Protection System
SRD_20 - Pantograph High Speed (HS2) | WP D21_Energy Supply Components | WP D10_Lighting
SRD_21 - Pantograph Conventional (CRN) | WP D21_Energy Supply Components | SRD_18 - Saloon Lighting
SRD_22 - Driver's Desk | WP D04_Drivers Cabin | SRD_19 - Exterior Lighting
SRD_23 - Vehicle Front End | WP D03_Vehicle Exterior Front End | WP D11_Toilet
SRD_24 - Windscreen Wiper | WP D36_Miscellaneous | SRD_16 - Toilet & Water System
SRD_25 - Windshield | WP D15_Windows and Windshield | WP D12_Signalling
SRD_26 - Master Controllers | WP D30_Train Control System | SRD_14 - Signalling System
SRD_27 - TCMS Driver Interface | WP D30_Train Control System | WP D13_Interiors
SRD_28 - Event Recorder | WP D32_Event Recorder | SRD_15 - Interiors Equipment
SRD_29 - WIFI System | WP D33_Communication and infotainment | WP D15_Windows and Windshield
SRD_30 - TCMS Electronics | WP D30_Train Control System | SRD_25 - Windshield
SRD_31 - Windows | WP D15_Windows and Windshield | SRD_31 - Windows
SRD_32 - Energy Meter System | WP D20_Energy measuring | WP D16_Inter-Vehicle Connections
SRD_33 - VCB | WP D21_Energy Supply Components | SRD_02 - Cab Coupler System
SRD_34 - Brake Resistor | WP D24_Braking Resistor | WP D17_Inter-Car Connections
SRD_35 - Battery | WP D28_Battery | SRD_03 - Inter-Car Coupler System
SRD_36 - Battery Charger | WP D27_Battery Charger | WP D18_Gangway
SRD_37 - Main Transformer | WP D21_Energy Supply Components | SRD_04 - Inter-car Gangway System
SRD_38 - Traction Converter | WP D22_Propulsion System | WP D19_Bogie / Running gear
SRD_39 - APS System | WP D26_Auxiliary Power Supply | SRD_43 - Motor Bogie
SRD_40 - Traction Motor | WP D23_Traction motor | SRD_44 - Trailer Bogie
SRD_41 - On-Board Server | WP D31_Diagnostics and Telediagnostics | WP D20_Energy measuring
SRD_42 - Carbody Shell | WP D01_Carbody and interfaces | SRD_32 - Energy Meter System
SRD_43 - Motor Bogie | WP D19_Bogie / Running gear | WP D21_Energy Supply Components
SRD_44 - Trailer Bogie | WP D19_Bogie / Running gear | SRD_20 - Pantograph High Speed (HS2)
SRD_45 - High Voltage Cables | WP D21_Energy Supply Components | SRD_21 - Pantograph Conventional (CRN)
SRD_46 - Electrical Connectors | WP D21_Energy Supply Components | SRD_33 - VCB
SRD_47 - UGMS | WP D36_Miscellaneous | SRD_37 - Main Transformer
SRD_45 - High Voltage Cables
SRD_46 - Electrical Connectors
WP D22_Propulsion System
SRD_38 - Traction Converter
WP D23_Traction motor
SRD_40 - Traction Motor
WP D24_Braking Resistor
SRD_34 - Brake Resistor
WP D26_Auxiliary Power Supply
SRD_39 - APS System
WP D27_Battery Charger
SRD_36 - Battery Charger
WP D28_Battery
SRD_35 - Battery
WP D30_Train Control System
SRD_26 - Master Controllers
SRD_27 - TCMS Driver Interface
SRD_30 - TCMS Electronics
WP D31_Diagnostics and Telediagnostics
SRD_41 - On-Board Server
WP D32_Event Recorder
SRD_28 - Event Recorder
WP D33_Communication and infotainment
SRD_11 - PIS
SRD_12 - APC (Automatic Passenger Counting) System
SRD_17 - CCTV System
SRD_29 - WIFI System
WP D36_Miscellaneous
SRD_24 - Windscreen Wiper
SRD_47 - UGMS
Grand Total